# SECTION 01041 PROJECT COORDINATION

## PART 1 - GENERAL

### REQUIREMENTS INCLUDED

    - Engineer will coordinate the work between Prime Contractors as required.

    - [The] [Each Prime] Contractor shall:

      - Coordinate work of his [own] employees and subcontractors.

      - Expedite his work to assure compliance with schedules.

      - [Coordinate his work with that of other Prime Contractors and work by Owner.]

      - Comply with orders and instructions of Engineer.

  - RELATED REQUIREMENTS

    - Section 01152:   Applications for Payment.

    - Section 01200:   Project Meetings.

    - Section 01310:   Construction Schedules.

    - Section 01340:   Shop Drawings, Product Data and Samples.

    - Section 01700:   Contract Closeout.

  - CONSTRUCTION ORGANIZATION AND START-UP

    - Engineer shall establish on-site lines of authority and communications:

      - Schedule and conduct pre-construction meeting and progress meetings as specified in Section.

      - Establish procedures for [intra-project communications]:

        - Submittals

        - Reports and records

        - Recommendations

        - Coordination of drawings

        - Schedules

        - Resolution of conflicts

      - Interpret Contract Documents:

### Transmit written interpretations to [Prime] Contractors, and to other concerned parties.

      - Assist in obtaining permits and approvals:

        - Verify	that	contractor[s]	and	subcontractors	have	obtained inspections for Work and for temporary facilities.

      - Control the use of Site:

        - Allocate space for [each Prime] Contractor's use for field offices, sheds, and work and storage areas.

      - Inspection and Testing:

        - Inspect work to assure performance in accord with requirements of Contract Documents.

        - Administer special testing and inspections of suspect Work.

        - Reject Work which does not comply withrequirements of Contract Documents.

  - CONTRACTOR'S DUTIES

    - Construction Schedules:

      - Prepare a detailed schedule of basic operations.

      - Monitor schedules as work progresses:

        - Identify potential variances between scheduled and probable completion dates or each phase.

        - Recommend to Owner adjustments in schedule to meet required completion dates.

        - Document changes in schedule; submit to Owner, Engineer and to involved subcontractors.

      - Observe work of each subcontractor to monitor compliance with schedule.

        - Verify that labor and equipment are adequate for the work and the schedule.

        - Verify that product procurement schedules are adequate.

        - Verify that product deliveries are adequate to maintain schedule.

        - Report noncompliance to Engineer, with recommendation for changes.

    - Process Shop Drawings, Product Data and Samples:

      - Prior to submittal to Engineer, review for compliance with Contract Documents:

        - Field dimensions and clearance dimensions.

        - Relation to available space.

        - Effect of any changes on the work of any subcontractor.

    - Prepare Coordination Drawings as required to resolve conflicts and to assure coordination of the work of, or affected by, mechanical and electrical trades, or by special equipment requirements.

      - Submit to Engineer.

      - Reproduce and distribute copies to concerned parties after Engineer review.

    - Maintain Reports and Records at Job Site, available to Engineer and Owner.

      - Daily log of progress of work.

      - Records

        - Contracts

        - Purchase orders

        - Materials and equipment records

        - Applicable handbooks, codes and standards

      - Maintain file of record documents

  - CONTRACTOR'S CLOSE-OUT DUTIES

    - At completion of Work, conduct an inspection to assure that:

      - Specified cleaning has been accomplished.

      - Temporary facilities have been removed from site.

    - Substantial Completion:

      - Conduct an inspection to develop a list of Work to be completed or corrected.

      - Assist Engineer in inspection.

      - Supervise correction and completion of work of subcontractors.

  - ENGINEER'S CLOSE-OUT DUTIES

    - Final Completion:

      - When [each] Contractor determines that Work is finally complete, conduct an inspection to verify completion of Work.

    - Administration of Contract closeout:

      - Receive and review contractor's final submittals.

      - Transmit to Owner with recommendations for action.

PART 2 - PRODUCTS

Not used.

PART 3 - EXECUTION

Not used.

END OF SECTION 01041