# SECTION 01310 CONSTRUCTION SCHEDULES

## PART 1 - GENERAL

### REQUIREMENTS INCLUDED

    - Promptly after award of the Contract, prepare and submit to Engineer estimated construction progress schedules for the Work, with subschedules of related activities which are essential to its progress.

    - Submit revised progress schedules to maintain proposed schedule within 30 days of work in place.

  - RELATED REQUIREMENTS

    - Conditions of the Contract.

    - Section 01010:  Summary of Work.

    - Section 01020:  Allowances.

    - Section 01041:  Project Coordination.

    - Section 01200:  Project Meetings.

    - Section 01340:  Shop Drawings.

  - FORM OF SCHEDULES

    - Prepare schedules in the form of:

      - Horizontal Bar Chart.

      - Network Analysis System.

      - Other Method Accepted by Owner.

    - Format of Listings: The chronological order of the start of each item of work.

  - CONTENT OF SCHEDULES

    - Construction Progress Schedule:

      - Show the complete sequence of construction by activity.

      - Show the dates for the beginning, and completion of each major element of construction.  Specifically list:

        - Site clearing.

        - Site utilities.

        - Foundation work.

        - Structural framing.

        - Subcontractor work.

        - Equipment installations.

        - Delivery of O & M Manuals.

        - Finishings.

        - Start-up

    - Submittals, Schedule for Shop Drawings, Product Data and Samples. Show:

      - The dates for Contractor's Submittals.

      - The dates revised submittals will be required from the Engineer.

    - Provide subschedules to define critical portions of prime schedules.

  - PROGRESS REVISIONS

    - Indicate progress of each activity to date of submission.

    - Show changes occurring since previous submission of schedule:

      - Major changes in scope.

      - Activities modified since previous submission.

      - Revised projections of progress and completion.

      - Other identifiable changes.

    - Provide a narrative report as needed to define:

      - Problem areas, anticipated delays, and the impact on the schedule.

      - Corrective action recommended, and its effect.

      - The effect of changes on schedules of other prime contractors.

  - SUBMISSIONS

    - Submit initial schedules within 10 days after the effective date of the Agreement.

      - Engineer will review schedules and return review copy within 10 days after receipt.

      - If required, resubmit within seven days after return of review copy.

    - With each application for payment, submit progress schedule if revised since last payment request.

    - Submit one reproducible transparency which will be returned to the Contractor, plus two copies which will be retained by the Engineer.

  - DISTRIBUTION

    - Distribute copies of the reviewed schedules to:

      - Job site file.

      - Subcontractors.

      - Other concerned parties.

    - Instruct recipients to report promptly to the Contractor, in writing, any problems anticipated by the projections shown in the schedules.

PART 2 - PRODUCTS

Not used.

PART 3 - EXECUTION

Not used.

END OF SECTION 01310